## Sheet1
Name of Country | Bahrain
Capacity | Identified Gap | National Action |  | External Support (WHO and others) | When
|  | Action | Agency
Legislative Infrastructure and Coordination mechanisms | legislation on surveillance and response to chemical events not available | Review of all legistelation, polcies, and plans.Establishment of multisectoral committee for chemical events | legal affairs of Supreme council of environement in collaboration with Legal affairs of ministry of Health as well as concern legal advisor. |  | 6-12 Months
| No operational public health plan for responding to chemical events |  | Civil Defence with other Parties. | Technical Support of WHO | 9 Months
| Insufficient coordination |  | Supreme council of environment, MOH and civil defence | Technical Support of WHOl UN | 1 year
Availability of reliable information, Poison Centers; information systems, risk communication and surveillance systems | Poisen Centre not available | 1.To Establish Apoison Centre 2.Mapping of poison faciliites 3.Assessment of facilities 4.Access to poison centers | Supreme council of environment. | Technical Support of WHOl UN | 1-2 years
| No reliable information | 1.Listing of possible chemical events 2. Invetory of chemical sites/installations 3.Exchange of informations
| 1. Poor risk communication plan | 2.Establishment/Revising communicatoin plan
Laboratory infrastructure and analytical capacity, and Emergency preparedness with mechanisms and infrastructure to respond to chemical incidents
| Environmental LAB needs improvement | 1.Assessment of lab facilities2.Identification of strenghts and weaknesses 3.Gap findings 4.Plan for enhancement 5.To Upgrade the Lab, fully Equipied,Manpower and conduct Training | Supreme council of environment | Technical Support of WHO withUN | 1 year